# Monash Primary School

Tuggeranong

# School Strategic Plan 
2025-2028

## Our vision, mission and values

### Vision

Monash Primary School students are capable, inclusive learners who are equipped with the skills, knowledge, and values needed to reach their full potential.

### Mission

Monash Primary School strives to create a caring and inclusive learning community with a strong focus on high-quality, evidence-based teaching. We hold high expectations for all learners and, through strong partnerships between school and home, foster a culture of Responsibility, Respect, Resilience, and Safety.

### Values

Monash Primary School is guided by four core values that shape the way we learn, work, and interact as staff, students, and community members: - Responsibility - Respect - Resilience - Safety

## Our improvement priorities

### Priority 1:  Improve student growth in writing

The statement below details our vision for how this priority will impact student outcomes.

- Students will see themselves as successful writers. - Students will benefit from teachers' understanding of evidence-based writing instruction and delivery. - Students will benefit from explicit and sequential writing instruction. - Students will receive targeted feedback to improve their writing.

### Targets and measures

Student learning data

| Target or measure | Source | Starting point |
| --- | --- | --- |
| Increase the percentage of Year 3 students in the Strong and Exceeding proficiency levels in Writing to 76%. | NAPLAN data available on Teaching and Learning Dashboard – NAPLAN Overview | Baseline of 72% was determined by averaging the percentage of students in the Strong and Exceeding proficiency levels of NAPLAN Writing 2023-2025. |
| Increase the percentage of Year 5 students in the Strong and Exceeding proficiency levels in Writing to 66% . | NAPLAN data available on Teaching and Learning Dashboard – NAPLAN Overview | Baseline of 51% was determined by averaging the percentage of students in the Strong and Exceeding proficiency levels in NAPLAN Writing 2023-2025. |

| #### Increase the average writing age in Years 2, 4, and 6 to meet student’s chronological age at the end of the year (Year 2: 8 years, Year 4: 10 years, Year 6: 12 years). | #### No More Marking data (2025), collected in March and October each year | #### Year 2: 6 years 10 months, Year 4: 9 years 1 months, Year 6: 9 years 8 months. |
| --- | --- | --- |

### Perception data

| Target or measure | Source | Starting point |
| --- | --- | --- |
| Increase the percentage of students who view themselves as capable and successful writers to 80% (yes responses) Survey question 1: I think I am a good writer Survey question 2: I know what a good piece of writing looks like. |  | School-based student survey (Successful writers) | Baseline data from Survey Question 1: Not yet: 11.3%, Maybe: 44.3%, Yes: 44.3%. Survey Question 2: Not really: 18.4%, I think so: 45.3%, Yes: 42%. |
| Increase the percentage of teachers who feel confident and independent in delivering high quality writing instruction, underpinned by a strong understanding of the content to 50%. Survey question: How confident are you in your understanding and application of evidence informed writing frameworks, such as the simple view of writing and the writing rope? |  | School-based teacher survey Confidence in the writing content and how to teach it | Baseline data from Survey Question 2: Not confident at all: 17.4%, Somewhat confident: 34.8%, Confident with support: 30.4%, Confident and independent: 17.4%, Highly Confident: 0%. |

School process data

| Target or measure | Source | Starting point |
| --- | --- | --- |
| By the end of the school plan, 100% of the Literacy Agreed Practices will be implemented in classrooms. |  | School based walk-through observation records | 85% of the Literacy Agreed Practices are being implemented in classrooms. |
| Increase average staff evaluation from PLC maturity matrix, from Evolving to Excelling in ‘Building Practice Excellence’. |  | PLC Maturity Matrix | Baseline staff average of evolving in ‘Building Practice Excellence’. |

## Our key improvement strategies

### Strategy 1: 	Build a school vision of what high quality writing instruction looks like at Monash School.

### Strategy 2: 	Deepen staff knowledge and practice in providing high quality writing instruction.

### Strategy 3: 	Embed evidence-based teaching practices to improve student writing outcomes.

## Endorsement

This Strategic Plan has been endorsed electronically by our Principal, Executive Education Leader and School Board.

### Principal

Name:  Matthew Holdway

Date: 12/11/2025

### Executive Education Leader

Name:  Steve Collins

Date: 12/11/2025

### School Board

| Members of School Board | - Matt Holdway - Tracey Hanson - Brooke Penna - Kim MacDonald (P & C Parent Rep) - Steven Anderson (Parent Rep) - Adam Smith (Parent Rep) - Tanya Young (Community Rep) |
| --- | --- |

Date: 12/11/2025